Sample Audit Data Collection Timeline—Intensive Approach

While an intensive week might include one or more focus groups, in this illustration the focus groups occur prior to the data-collection week. Team members have a summary of the key themes available as a reference to help inform the observations, interviews, other activities, and analysis that they will be engaged in during the week. See Section 3 of Logistics Guide regarding role of team members in conducting focus groups with survivors.

| 4 months prior | Audit Coordinator and Audit consultant identify: Current system, organizational structures, policies Key players and policy makers Interviews & observations needed List of texts needed Process for securing access to various texts to be analyzed Dates for 2-day planning visit Dates for Audit week Meetings rooms and other space Possible Audit team members |
| --- | --- |
| 3 months prior | Audit Coordinator and Praxis consultant: Assembles and sends Praxis the texts identified above Confirms Audit team members Schedules and reserves meeting space Makes preliminary arrangements for observations and interviews Draft preliminary timetable for Audit week Begin text analysis |
| 6 - 8 weeks prior | Audit Coordinator and Praxis consultant: Conduct a 1- or 2-day planning visit and training with Audit team: What is an Audit? Map the system Determine team assignments Determine if anyone is missing from the team Finalize documents to review Review and finalize interviews and observations Conduct victim/survivor focus groups Collect statistics Finalize schedule for Audit week |
| 2 weeks prior | Audit Coordinator distributes Audit packets that include: Summary of focus group key themes Copies of preliminary text analysis results Team assignments & individual schedules Copies of reading materials: policies, statutes, theory Each Audit team member: Reads & analyzes text analysis Becomes familiar with policies, etc. of his/her assigned area |

Audit Week

| Day One | Praxis meeting with Audit Coordinator Afternoon reception for Audit team (introductions, Audit overview, distribute and review schedule) Praxis observation |
| --- | --- |
| Day Two | Breakfast meeting with policy makers (introductions, what’s an Audit, why are we here, set the stage for interviews and reporting preliminary findings at the end of the week) Beginning at 9:30 AM, Audit team meets together: Refresher on text analysis, demonstration interviews, and guidelines for observations Evening observations Evening interviews, as appropriate |
| Day Three and Day Four | Meet separately in small working groups; individual assignments throughout day and evening: Text analysis Observations Interviews |
| Day Five | Whole Audit team meets in small working groups to develop preliminary findings and recommendations. Each group presents its work to the full team for discussion and modification. Present preliminary findings Option A: The team meets individually with agency administrators to report back it’s recommendations for that agency Option B: The team meets with all agency administrators and other policy makers to present all preliminary findings. |
| Post-Audit Follow-up | Wrap-up data collection to fill in gaps in team’s knowledge or confirm preliminary findings. One – three months: final report finished |